## Sheet1
Sl No | Issue list | Status | Remarks
1 | The CEO Login/ Manager – Sales Login should have the dashboard feature of a sales person + the feature of looking at junior sales persons dashboard and report. | Completed
2 | The Dashboard of CEO Should show combined sales from Pan India. Whereas the dashboard of the Sale Manager should show the combined sales of a team and the dash board of a sales person should show the revenue generated by themselves. | Completed
3 | In Create account the – Progress type should have “existing” option also. | Completed
4 | Manage Account Details – Uploading “Visiting card” should be a mandatory field | Completed
5 | There is a bit lapse in closing pop-up windows. It only closes if Esc is pressed. | Completed
6 | Create Enquiry - Services field should be multi select field | Completed
7 | Create Job Schedule need to be put along with Job Type. – sorted for call. | Completed
8 | If the Job TYPE is other then the schedule type should also be other. | Completed
9 | Update Meeting Schedule – Meeting Status – Card cannot be uploaded | Completed
10 | Report Generation Feature needs to be integrated. | Completed
11 | No Option to see which accounts are there listed with PMR. Please integrate. Currently can only view the accounts A particular salesperson has put himself. | Completed
12 | A sales person should be able to search account from PMR Database and request accounts ( Both HOT or Cold from CEO) He should be able to see the ( Name of Account, Status (HOT/COLD/Existing), And Sales Person Name if it is tagged to someone) | Completed
13 | For Create Enquiry the First Field should be Enquiry Type. | Completed
14 | If the person chooses corporate only then the Account name should appear. | Completed
15 | In update the Schedule – under survey status the spelling of survey is wrong. | Completed
16 | If survey is done how will update survey show completed | Completed
17 | If another employee is attending the meeting with the employee making the meeting request then he should be able to first accept the meeting and then tick mark on the meeting update section to complete the process | Completed
18 | There should be an option to set self-reminders also. | Completed
19 | Option for Marketing Collateral Missing – We want to put PPT’s, Company profile, Coverage Copies, Manual etc so that the sales person can download from there directly. | Phase 2 | It is document management system
20 | Also, If a person skips a call time updating or meeting updating a notification should show on Sales person’s dashboard. If it is skipped for more than 2 weeks then the notification should show on both the immediate reporting manager and employee dashboard. | WIP
21 | If targets are achieved then a notification should go out to both the target giver and the receiver. | WIP
22 | Changes on the dashboard. Compact dashboard. | Pending

## Sheet4
1 | Department | Is super Admin not fetched
2 | Todays Meeting | One week chart(small chart |  | small chart
3 | Total Sale | 12 Month |  | small chart
4 | Hot Account | Graph | Not respond client site | small chart
|  | Click | Drill down
5 | Cold Account
6 | Enquiry | Graph | One month | small chart
7 | ConvertionRate | Graph | One month | small chart
8 | Account | graph | yearly monthwise | small chart
| Billing | graph | yearly monthwise | small chart
9 | Target |  |  | small chart